## Dashboard
Project Management Tracker | [10 empty] | HELPERS
PROJECTS |  |  | TASKS |  |  | OVERALL PROGRESS |  |  | OVERDUE TASKS
Due date passed, not done
Rows on the Projects sheet |  |  | Rows on the Task List |  |  | Average of task % complete |  |  | Work these first
DUE IN 14 DAYS |  |  | PROJECTS AT RISK |  |  | WAITING |  |  | COMPLETED
Not completed |  |  | Overdue or due soon and behind |  |  | Blocked on someone else |  |  | Closed tasks
Look at Upcoming below |  |  | Health on Projects sheet |  |  | Nudge the owner |  |  | Keep this number moving
UPCOMING (NEXT 14 DAYS) | [5 empty] | OVERDUE
Task | Project | Due | Owner |  | Status | Task | Project | Due | Owner | Days late
PROGRESS BY PROJECT | [5 empty] | TASKS BY STATUS
Start on Projects, add tasks, then live here. Overdue is red until Status is Completed. See Instructions for the 5-minute start.
Project | Progress |  | Status | Count
Not Started
In Progress
Waiting
On Hold
Completed

## Projects
Projects | [11 empty] | DROPDOWN LISTS | Edit these if you need extra options.
One row per project. % Complete, task counts, and Health come from the Task List. Blue = type. Gray = calculated. | [11 empty] | Maya Chen | People (Assigned to / Owner)
Jordan Blake
Project name | Owner / lead | Start | End | Status | Priority | % Complete | Tasks | Open | Overdue | Notes | Health | Sam Okonkwo
Website Redesign | Maya Chen | 2026-07-01 | 2026-09-30 | In Progress | High |  |  |  |  | Public site + CMS |  | Riley Patel
Q3 Client Launch | Jordan Blake | 2026-08-01 | 2026-08-26 | In Progress | High |  |  |  |  | Acme Co. go-live |  | Alex Rivera
Hiring Pipeline | Sam Okonkwo | 2026-08-01 | 2026-10-15 | On Hold | Medium |  |  |  |  | Paused pending budget
Brand Guidelines | Riley Patel | 2026-09-01 | 2026-10-31 | Not Started | Low |  |  |  |  | Internal + client kit |  | Not Started | Project status
In Progress
On Hold
Completed
[12 empty] | Not Started | Task status
In Progress
Waiting
On Hold
Completed
[12 empty] | High | Priority
Medium
Low
[12 empty] | Upcoming | Milestone status
Done
TOTAL | [11 empty] | Missed
Add a project in the next blank blue row. Then add tasks on the Task List and pick this name from the Project dropdown.
Formulas:
Health = IF([Projects]="","",IF([Status]="Completed","Done",IF(AND([End]<>"",[End]<TODAY()),"Overdue",IF(AND([End]<>"",[End]<=TODAY()+14,N(G5)<0.75),"At risk","On track"))))
Note on G4: Average of task % on the Task List. Completed tasks count as 100%.
Note on L4: Done / Overdue (end date passed) / At risk (due within 14 days and under 75%) / On track.

## Task List
Task List
One row per task. Pick the Project from the dropdown so Dashboard and project % stay in sync. Filter and sort freely.
Task name | Project | Assigned to | Priority | Status | Start | Due | % Complete | Est. hrs | Actual hrs | Notes | Days left | Overdue?
Kickoff workshop | Website Redesign | Maya Chen | High | Completed | 2026-07-01 | 2026-07-03 | 100% | 6 | 5.5
Sitemap and IA | Website Redesign | Maya Chen | High | Completed | 2026-07-06 | 2026-07-18 | 100% | 12 | 14
Visual mockups | Website Redesign | Riley Patel | High | In Progress | 2026-07-20 | 2026-08-15 | 70% | 24 | 18 | Homepage + 3 inner
Stakeholder review | Website Redesign | Maya Chen | High | Waiting | 2026-08-05 | 2026-08-12 | 40% | 3 | 2 | Waiting on legal
Homepage build | Website Redesign | Jordan Blake | High | In Progress | 2026-08-04 | 2026-08-22 | 40% | 20 | 8
Dev handoff packet | Website Redesign | Jordan Blake | Medium | Not Started | 2026-08-18 | 2026-08-29 | 0% | 6
CMS training | Website Redesign | Maya Chen | Medium | Not Started | 2026-09-08 | 2026-09-12 | 0% | 4
QA pass | Website Redesign | Sam Okonkwo | High | Not Started | 2026-09-15 | 2026-09-25 | 0% | 10
Asset list from client | Q3 Client Launch | Jordan Blake | High | Waiting | 2026-08-01 | 2026-08-08 | 50% | 2 | 1 | Logos still missing
Landing page copy | Q3 Client Launch | Maya Chen | High | Completed | 2026-08-01 | 2026-08-10 | 100% | 8 | 7
Landing page build | Q3 Client Launch | Jordan Blake | High | In Progress | 2026-08-08 | 2026-08-20 | 55% | 16 | 10
Email sequence | Q3 Client Launch | Riley Patel | Medium | In Progress | 2026-08-11 | 2026-08-18 | 30% | 8 | 3
QA / UAT | Q3 Client Launch | Sam Okonkwo | High | Not Started | 2026-08-19 | 2026-08-25 | 0% | 6
Launch checklist | Q3 Client Launch | Jordan Blake | High | Not Started | 2026-08-26 | 2026-08-28 | 0% | 3
Role scorecard | Hiring Pipeline | Sam Okonkwo | Medium | Completed | 2026-08-01 | 2026-08-04 | 100% | 4 | 3
Post the role | Hiring Pipeline | Sam Okonkwo | Medium | Completed | 2026-08-04 | 2026-08-05 | 100% | 2 | 2
Screen resumes | Hiring Pipeline | Sam Okonkwo | Medium | On Hold | 2026-08-06 | 2026-08-20 | 20% | 8 | 2 | Budget hold
First interviews | Hiring Pipeline | Maya Chen | Medium | On Hold | 2026-08-18 | 2026-09-05 | 0% | 10
Competitive scan | Brand Guidelines | Riley Patel | Low | Not Started | 2026-09-01 | 2026-09-12 | 0% | 8
Type and color system | Brand Guidelines | Riley Patel | Medium | Not Started | 2026-09-15 | 2026-10-03 | 0% | 16
Component examples | Brand Guidelines | Jordan Blake | Low | Not Started | 2026-10-06 | 2026-10-24 | 0% | 12
Internal review deck | Brand Guidelines | Riley Patel | Low | Not Started | 2026-10-20 | 2026-10-31 | 0% | 6
TOTAL
Add a task in the next blank blue row. Days left is negative when overdue. Use the filter arrows to focus on one project or person.
Formulas:
Days left = IF(OR([Task name]="",[Due]=""),"",[Due]-TODAY())
Overdue? = IF([Task name]="","",IF(AND([Due]<>"",[Due]<TODAY(),[Status]<>"Completed"),"Yes",""))
Note on B4: Must match a name on the Projects sheet. Add the project there first.
Note on H4: 0 to 100%. When Status is Completed this is treated as 100% even if you leave it blank.

## Timeline
Timeline / Gantt
Timeline start (Monday) |  |  | 2026-08-10 | Each column is one week. A block means the task is scheduled that week. Color follows Status. First 40 tasks from the Task List.
Task | Project | Start | Due | Status
Slide the window by changing Timeline start. Overlaps are expected — that is the point. Empty task rows stay blank.
Note on D2: First Monday of the Gantt. Change this to slide the window. 18 weeks are shown.

## Milestones
Milestones
Key dates only — not every task. Mark Done when it ships. Missed is for a date that passed without a finish.
Milestone | Project | Due | Status | Owner | Notes | Days left
Design approval | Website Redesign | 2026-08-15 | Upcoming | Maya Chen | Sign-off on mockups
Development complete | Website Redesign | 2026-09-20 | Upcoming | Jordan Blake
Site go-live | Website Redesign | 2026-09-30 | Upcoming | Maya Chen | Public launch
Client UAT starts | Q3 Client Launch | 2026-08-19 | Upcoming | Sam Okonkwo
Public launch | Q3 Client Launch | 2026-08-28 | Upcoming | Jordan Blake | Do not slip
Asset lock | Q3 Client Launch | 2026-08-08 | Missed | Jordan Blake | Client late
Offer out | Hiring Pipeline | 2026-10-01 | Upcoming | Sam Okonkwo
First draft | Brand Guidelines | 2026-10-10 | Upcoming | Riley Patel
Final delivery | Brand Guidelines | 2026-10-31 | Upcoming | Riley Patel
Formulas:
Days left = IF(OR([Milestone]="",[Due]=""),"",[Due]-TODAY())

## Instructions
How to use this template
A simple project system: projects, tasks, milestones, and a week-by-week timeline. No training required.
1. Five-minute start
1. Open Projects. Replace the sample rows with your projects: name, owner, start, end, status, priority.
2. Open Task List. Delete or overwrite the sample. Each task needs a name, a Project from the dropdown, an owner, dates, and a status.
3. Add the dates that actually matter on Milestones (launch, sign-off, go-live).
4. Live on the Dashboard. Overdue is red. Upcoming is the next two weeks. At risk means a project end date is close and progress is thin.
5. Open Timeline to see the next 18 weeks. Change Timeline start (a Monday) to slide the window.
2. What each tab does
Dashboard — counts, progress, overdue, upcoming. Nothing to type.
Projects — the portfolio. % Complete and Health calculate from tasks.
Task List — the work. Filter by project or person with the arrows on the header row.
Timeline / Gantt — same tasks, drawn across weeks. Color = status.
Milestones — the few dates you would put on a slide.
Instructions — this guide.
3. Color key
Blue cell = type. Gray cell = formula.
Green = completed. Blue row = in progress. Amber = waiting or at risk. Purple = on hold. Red = overdue or missed.
4. Add a project or task
Add a project on Projects first (next blank blue row). Then on Task List, pick that name from the Project dropdown. The Dashboard and the project % update themselves.
Add people or statuses in column N on Projects if the dropdown is missing a name.
5. How Health is decided
Done — project Status is Completed. Overdue — end date is in the past and it is not Done. At risk — end date is within 14 days and % Complete is under 75%. Otherwise On track.
6. Google Sheets
Upload this file to Drive. Formulas, dropdowns, and the Gantt blocks come across. Sheet protection often does not — the blue/gray colors still show what to edit. If a dropdown is missing, point it at Projects column N.
Empty blue rows are unused. You do not need to fill the sheet.